## Detailed_Iterations
Iteration | Event | Duration (hours) | Participants | Date (Wednesday group) | Day (Wednesday group) | Date (Thursday group) | Day (Thursday group) | Date (Friday group) | Day (Friday group)
Sprint 0 | Team definition | 3 | Scrum Master - Scrum Team - Product Owner | 2025-07-16 | wednesday | 2025-07-17 | thursday | 2025-07-18 | friday
| Product Vision - Project Planning | 3 | Scrum Master - Scrum Team - (Product Owner) | 2025-07-17 | thursday | 2025-07-18 | friday | 2025-07-19 | saturday
Sprint 1 | Sprint Planning (product vision board, requirements prioritization, requirements specification) | 4 | Scrum Master - Scrum Team - Product Owner | 2025-07-18 | friday | 2025-07-19 | saturday | 2025-07-20 | sunday
|  |  |  | 2025-07-19 | saturday | 2025-07-20 | sunday | 2025-07-21 | monday
| Design (domain model) | 2 | Scrum Master - Scrum Team - (Product Owner) | 2025-07-20 | sunday | 2025-07-21 | monday | 2025-07-22 | tuesday
|  |  |  | 2025-07-21 | monday | 2025-07-22 | tuesday | 2025-07-23 | wednesday
| Weekly 1 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-07-22 | tuesday | 2025-07-23 | wednesday | 2025-07-24 | thursday
|  |  |  | 2025-07-23 | wednesday | 2025-07-24 | thursday | 2025-07-25 | friday
|  |  |  | 2025-07-24 | thursday | 2025-07-25 | friday | 2025-07-26 | saturday
| Development | 3 | Scrum Team | 2025-07-25 | friday | 2025-07-26 | saturday | 2025-07-27 | sunday
|  |  |  | 2025-07-26 | saturday | 2025-07-27 | sunday | 2025-07-28 | monday
| Test | 1 | Scrum Team | 2025-07-27 | sunday | 2025-07-28 | monday | 2025-07-29 | tuesday
|  |  |  | 2025-07-28 | monday | 2025-07-29 | tuesday | 2025-07-30 | wednesday
| Weekly 2 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-07-29 | tuesday | 2025-07-30 | wednesday | 2025-07-31 | thursday
|  |  |  | 2025-07-30 | wednesday | 2025-07-31 | thursday | 2025-08-01 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-07-31 | thursday | 2025-08-01 | friday | 2025-08-02 | saturday
| Development | 3 | Scrum Team | 2025-08-01 | friday | 2025-08-02 | saturday | 2025-08-03 | sunday
|  |  |  | 2025-08-02 | saturday | 2025-08-03 | sunday | 2025-08-04 | monday
| Test | 1 | Scrum Team | 2025-08-03 | sunday | 2025-08-04 | monday | 2025-08-05 | tuesday
|  |  |  | 2025-08-04 | monday | 2025-08-05 | tuesday | 2025-08-06 | wednesday
| Weekly 3 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-08-05 | tuesday | 2025-08-06 | wednesday | 2025-08-07 | thursday
|  |  |  | 2025-08-06 | wednesday | 2025-08-07 | thursday | 2025-08-08 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-08-07 | thursday | 2025-08-08 | friday | 2025-08-09 | saturday
|  |  |  | 2025-08-08 | friday | 2025-08-09 | saturday | 2025-08-10 | sunday
|  |  |  | 2025-08-09 | saturday | 2025-08-10 | sunday | 2025-08-11 | monday
|  |  |  | 2025-08-10 | sunday | 2025-08-11 | monday | 2025-08-12 | tuesday
|  |  |  | 2025-08-11 | monday | 2025-08-12 | tuesday | 2025-08-13 | wednesday
| Weekly 4 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-08-12 | tuesday | 2025-08-13 | wednesday | 2025-08-14 | thursday
| Sprint Review | 2 | Scrum Master - Scrum Team - Product Owner | 2025-08-13 | wednesday | 2025-08-14 | thursday | 2025-08-15 | friday
| Sprint Retrospective (What should we continue to do (best practices)? What should we start doing (process improvements)? What should we stop doing (process problems and bottlenecks)?) | 2 | Scrum Master - Scrum Team | 2025-08-14 | thursday | 2025-08-15 | friday | 2025-08-16 | saturday
Sprint 2 | Sprint Planning (requisitos para Sprint 2 reportados en Backlog) | 4 | Scrum Master - Scrum Team - Product Owner | 2025-08-15 | friday | 2025-08-16 | saturday | 2025-08-17 | sunday
|  |  |  | 2025-08-16 | saturday | 2025-08-17 | sunday | 2025-08-18 | monday
| Design (diagrama de alto nivel) | 2 | Scrum Master - Scrum Team - (Product Owner) | 2025-08-17 | sunday | 2025-08-18 | monday | 2025-08-19 | tuesday
|  |  |  | 2025-08-18 | monday | 2025-08-19 | tuesday | 2025-08-20 | wednesday
| Weekly 5 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-08-19 | tuesday | 2025-08-20 | wednesday | 2025-08-21 | thursday
|  |  |  | 2025-08-20 | wednesday | 2025-08-21 | thursday | 2025-08-22 | friday
|  |  |  | 2025-08-21 | thursday | 2025-08-22 | friday | 2024-08-23 | saturday
| Development (debe estar el archivo requirements.txt y los requisitos del Backlog en estado In Progress) | 3 | Scrum Team | 2025-08-22 | friday | 2024-08-23 | saturday | 2025-08-24 | sunday
|  |  |  | 2024-08-23 | saturday | 2025-08-24 | sunday | 2025-08-25 | monday
| Test | 1 | Scrum Team | 2025-08-24 | sunday | 2025-08-25 | monday | 2025-08-26 | tuesday
|  |  |  | 2025-08-25 | monday | 2025-08-26 | tuesday | 2025-08-27 | wednesday
| Weekly 6 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-08-26 | tuesday | 2025-08-27 | wednesday | 2025-08-28 | thursday
|  |  |  | 2025-08-27 | wednesday | 2025-08-28 | thursday | 2025-08-29 | friday
| Integration | 1 | Scrum Team | 2025-08-28 | thursday | 2025-08-29 | friday | 2025-08-30 | saturday
| Development | 2 | Scrum Team | 2025-08-29 | friday | 2025-08-30 | saturday | 2025-08-31 | sunday
|  |  |  | 2025-08-30 | saturday | 2025-08-31 | sunday | 2025-09-01 | monday
| Test | 1 | Scrum Team | 2025-08-31 | sunday | 2025-09-01 | monday | 2025-09-02 | tuesday
|  |  |  | 2025-09-01 | monday | 2025-09-02 | tuesday | 2025-09-03 | wednesday
| Weekly 7 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-09-02 | tuesday | 2025-09-03 | wednesday | 2025-09-04 | thursday
|  |  |  | 2025-09-03 | wednesday | 2025-09-04 | thursday | 2025-09-05 | friday
| Integration | 1 | Scrum Team | 2025-09-04 | thursday | 2025-09-05 | friday | 2025-09-06 | saturday
|  |  |  | 2025-09-05 | friday | 2025-09-06 | saturday | 2025-09-07 | sunday
|  |  |  | 2025-09-06 | saturday | 2025-09-07 | sunday | 2025-09-08 | monday
|  |  |  | 2025-09-07 | sunday | 2025-09-08 | monday | 2025-09-09 | tuesday
|  |  |  | 2025-09-08 | monday | 2025-09-09 | tuesday | 2025-09-10 | wednesday
| Weekly 8 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 |  | 2025-09-09 | tuesday | 2025-09-10 | wednesday | 2025-09-11 | thursday
| Sprint Review | 2 | Scrum Master - Scrum Team - Product Owner | 2025-09-10 | wednesday | 2025-09-11 | thursday | 2025-09-12 | friday
| Sprint Retrospective (What should we continue to do (best practices)? What should we start doing (process improvements)? What should we stop doing (process problems and bottlenecks)?) | 2 | Scrum Master - Scrum Team | 2025-09-11 | thursday | 2025-09-12 | friday | 2025-09-13 | saturday
Sprint 3 | Sprint Planning (requisitos para Sprint 3 reportados en Backlog) | 4 | Scrum Master - Scrum Team - Product Owner | 2025-09-12 | friday | 2025-09-13 | saturday | 2025-09-14 | sunday
|  |  |  | 2025-09-13 | saturday | 2025-09-14 | sunday | 2025-09-15 | monday
| Design | 2 | Scrum Master - Scrum Team - (Product Owner) | 2025-09-14 | sunday | 2025-09-15 | monday | 2025-09-16 | tuesday
|  |  |  | 2025-09-15 | monday | 2025-09-16 | tuesday | 2025-09-17 | wednesday
| Weekly 9 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-09-16 | tuesday | 2025-09-17 | wednesday | 2025-09-18 | thursday
|  |  |  | 2025-09-17 | wednesday | 2025-09-18 | thursday | 2025-09-19 | friday
|  |  |  | 2025-09-18 | thursday | 2025-09-19 | friday | 2025-09-20 | saturday
| Development | 3 | Scrum Team | 2025-09-19 | friday | 2025-09-20 | saturday | 2025-09-21 | sunday
|  |  |  | 2025-09-20 | saturday | 2025-09-21 | sunday | 2025-09-22 | monday
| Test | 1 | Scrum Team | 2025-09-21 | sunday | 2025-09-22 | monday | 2025-09-23 | tuesday
|  |  |  | 2025-09-22 | monday | 2025-09-23 | tuesday | 2025-09-24 | wednesday
| Weekly 10 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-09-23 | tuesday | 2025-09-24 | wednesday | 2025-09-25 | thursday
|  |  |  | 2025-09-24 | wednesday | 2025-09-25 | thursday | 2025-09-26 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-09-25 | thursday | 2025-09-26 | friday | 2025-09-27 | saturday
| Development | 3 | Scrum Team | 2025-09-26 | friday | 2025-09-27 | saturday | 2025-09-28 | sunday
|  |  |  | 2025-09-27 | saturday | 2025-09-28 | sunday | 2025-09-29 | monday
| Test | 1 | Scrum Team | 2025-09-28 | sunday | 2025-09-29 | monday | 2025-09-30 | tuesday
|  |  |  | 2025-09-29 | monday | 2025-09-30 | tuesday | 2025-10-01 | wednesday
| Weekly 11 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-09-30 | tuesday | 2025-10-01 | wednesday | 2025-10-02 | thursday
|  |  |  | 2025-10-01 | wednesday | 2025-10-02 | thursday | 2025-10-03 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-10-02 | thursday | 2025-10-03 | friday | 2025-10-04 | saturday
|  |  |  | 2025-10-03 | friday | 2025-10-04 | saturday | 2025-10-05 | sunday
|  |  |  | 2025-10-04 | saturday | 2025-10-05 | sunday | 2025-10-06 | monday
|  |  |  | 2025-10-05 | sunday | 2025-10-06 | monday | 2025-10-07 | tuesday
|  |  |  | 2025-10-06 | monday | 2025-10-07 | tuesday | 2025-10-08 | wednesday
|  |  |  | 2025-10-07 | tuesday | 2025-10-08 | wednesday | 2025-10-09 | thursday
|  |  |  | 2025-10-08 | wednesday | 2025-10-09 | thursday | 2025-10-10 | friday
|  |  |  | 2025-10-09 | thursday | 2025-10-10 | friday | 2025-10-11 | saturday
|  |  |  | 2025-10-10 | friday | 2025-10-11 | saturday | 2025-10-12 | sunday
|  |  |  | 2025-10-11 | saturday | 2025-10-12 | sunday | 2025-10-13 | monday
|  |  |  | 2025-10-12 | sunday | 2025-10-13 | monday | 2025-10-14 | tuesday
|  |  |  | 2025-10-13 | monday | 2025-10-14 | tuesday | 2025-10-15 | wednesday
| Weekly 12 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-10-14 | tuesday | 2025-10-15 | wednesday | 2025-10-16 | thursday
| Sprint Review | 2 | Scrum Master - Scrum Team - Product Owner | 2025-10-15 | wednesday | 2025-10-16 | thursday | 2025-10-17 | friday
| Sprint Retrospective (What should we continue to do (best practices)? What should we start doing (process improvements)? What should we stop doing (process problems and bottlenecks)?) | 2 | Scrum Master - Scrum Team | 2025-10-16 | thursday | 2025-10-17 | friday | 2025-10-18 | saturday
Sprint 4 | Sprint Planning | 4 | Scrum Master - Scrum Team - Product Owner | 2025-10-17 | friday | 2025-10-18 | saturday | 2025-10-19 | sunday
|  |  |  | 2025-10-18 | saturday | 2025-10-19 | sunday | 2025-10-20 | monday
| Design | 2 | Scrum Master - Scrum Team - (Product Owner) | 2025-10-19 | sunday | 2025-10-20 | monday | 2025-10-21 | tuesday
|  |  |  | 2025-10-20 | monday | 2025-10-21 | tuesday | 2025-10-22 | wednesday
| Weekly 13 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-10-21 | tuesday | 2025-10-22 | wednesday | 2025-10-23 | thursday
|  |  |  | 2025-10-22 | wednesday | 2025-10-23 | thursday | 2025-10-24 | friday
|  |  |  | 2025-10-23 | thursday | 2025-10-24 | friday | 2025-10-25 | saturday
| Development | 3 | Scrum Team | 2025-10-24 | friday | 2025-10-25 | saturday | 2025-10-26 | sunday
|  |  |  | 2025-10-25 | saturday | 2025-10-26 | sunday | 2025-10-27 | monday
| Test | 1 |  | 2025-10-26 | sunday | 2025-10-27 | monday | 2025-10-28 | tuesday
|  |  |  | 2025-10-27 | monday | 2025-10-28 | tuesday | 2025-10-29 | wednesday
| Weekly 14 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-10-28 | tuesday | 2025-10-29 | wednesday | 2025-10-30 | thursday
|  |  |  | 2025-10-29 | wednesday | 2025-10-30 | thursday | 2025-10-31 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-10-30 | thursday | 2025-10-31 | friday | 2025-11-01 | saturday
| Development | 3 | Scrum Team | 2025-10-31 | friday | 2025-11-01 | saturday | 2025-11-02 | sunday
|  |  |  | 2025-11-01 | saturday | 2025-11-02 | sunday | 2025-11-03 | monday
| Test | 1 | Scrum Team | 2025-11-02 | sunday | 2025-11-03 | monday | 2025-11-04 | tuesday
|  |  |  | 2025-11-03 | monday | 2025-11-04 | tuesday | 2025-11-05 | wednesday
| Weekly 15 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-11-04 | tuesday | 2025-11-05 | wednesday | 2025-11-06 | thursday
|  |  |  | 2025-11-05 | wednesday | 2025-11-06 | thursday | 2025-11-07 | friday
| Integration | 1 | Scrum Master - Scrum Team | 2025-11-06 | thursday | 2025-11-07 | friday | 2025-11-08 | saturday
|  |  |  | 2025-11-07 | friday | 2025-11-08 | saturday | 2025-11-09 | sunday
|  |  |  | 2025-11-08 | saturday | 2025-11-09 | sunday | 2025-11-10 | monday
|  |  |  | 2025-11-09 | sunday | 2025-11-10 | monday | 2025-11-11 | tuesday
|  |  |  | 2025-11-10 | monday | 2025-11-11 | tuesday | 2025-11-12 | wednesday
| Weekly 16 (What work did you complete last week? Are you facing any problem or issues? What have you planned for this week?) | 0.5 | Scrum Master - Scrum Team | 2025-11-11 | tuesday | 2025-11-12 | wednesday | 2025-11-13 | thursday
| Sprint Review | 2 | Scrum Master - Scrum Team - Product Owner | 2025-11-12 | wednesday | 2025-11-13 | thursday | 2025-11-14 | friday
| Sprint Retrospective (What should we continue to do (best practices)? What should we start doing (process improvements)? What should we stop doing (process problems and bottlenecks)?) | 2 | Scrum Master - Scrum Team | 2025-11-13 | thursday | 2025-11-14 | friday | 2025-11-15 | saturday
93
81
243
| Dedicación esperada | 96 | 48
2
96

## Schedule_Summary
ST0251 - Proyecto Integrador 1 - 2025-2
Iteration | Date | Activities | Evaluation | %
SPRINT 0 Wednesday group: 16/07 - 17/07 Thursday group: 17/07 - 18/07 Friday group: 18/07 - 19/07 | 14/07/2025 - 18/07/2025 | 1.1. Course presentation 1.2. Course schedule 1.3. Pacto pedagógico 1.4. Teams definition (3 to 5 members) |  |  | Entregas en inglés, diagramas y código
|  | 1.5. MVP and Agile practices 1.6. Product vision (project definition including (Data Analytics, web development with Django) | Tarea 1: Define the working team and register it in the team file. Tarea 2: Make the Product Vision board. Tarea 3: Collect information to validate the problem to be solved. |  | Revisar cómo se maneja en back y que no se hagan ciertas operaciones en el front
SPRINT 1 Wednesday group: 18/07 - 14/08 Thursday group: 19/07 - 15/08 Friday group: 20/07 - 16/08 | 21/07/2025 - 25/07/2025 | 2.1. Gestión de proyecto (GitHub) 2.2. Priorización de requisitos 2.3. Modelo de Dominio Plantilla Entrega 1 | Reunión con cada equipo para validar la idea |  | Revisar que los diagramas se hagan previamente
|  | 2.4. Plantilla de especificación de requisitos (Soporte científico que se puede leer para entender el origen de la plantilla) | Tarea 1: Crear el proyecto en GitHub Tarea 2: Priorizar 20 requisitos (indicar la técnica de priorización y el sprint en el que se desarrollarán) y registrarlos en la Wiki Tarea 3: Hacer el modelo de dominio y registrarlo en la Wiki |  | Fortalecer parte algorítmica y de estructuras de datos
|  | 2.5. Plantilla requisitos (Excel con ejemplos) | Tarea 4: Leer el artículo sobre la plantilla de especificación de requisitos Tarea 5: Especificar los 20 requisitos priorizados utilizando la plantilla de especificación de requisitos y registrarlos en la Wiki |  | Definir y llenar la BD desde el inicio
|  | 2.6. Plantilla de especificación de requisitos (vídeo con explicación) [https://eafit-my.sharepoint.com/:v:/g/personal/pvallej3_eafit_edu_co/EU_UC2Meag9Nob4d5oxaLxMBt4nNB885Avx5NRLX_-CU_w?e=z4sfPi] | Tarea 6: Empezar a trabajar en la plantilla de Entrega 1
| 28/07/2025 - 01/08/2025 | Git y GitHub | Tarea 1: Registrar los requisitos del Sprint 1 en el Backlog (cada requisito debe tener título, descripción detallada usando la plantilla de especificación de requisitos y responsable) Tarea 2: Aplicar los conceptos vistos en el taller para iniciar con el desarrollo del proyecto Tarea 3: Avanzar en la plantilla de Entrega 1
|  | Django | Workshop 1 (Git, GitHub, Django) | 5
| 04/08/2025 - 08/08/2025 | 4.1. Elevator Pitch | Deliverable 1: Problem, requirements, high-level architecture, proof of concept Plazo hasta el domingo, en la Wiki | 20
|  | 4.2. Diseño de Alto Nivel |  |  | 07/08/2025 festivo. Se debe definir una estrategia para realizar las actividades de la clase. Sugerencia grupo jueves: Realizar asesorías en un espacio diferente al de la clase.
4.3. Categorías de aplicaciones
|  | Seguimiento a equipos | Tarea 1: Continuar con el desarrollo de los requisitos del proyecto y hacer commits en el repositorio Tarea 2: Realizar el diagrama de alto nivel y registrarlo en la Wiki
| 11/08/2025 - 15/08/2025 | Review | Review 1: 1. Pitch [3 min.]: One team member presents the project or team name, team members, problem/opportunity/need, proposed solution, added value, and project status. 2. Demo [12 min.]: Each team member presents the operation of the assigned requirements 3. Questions [5 min.]: Teacher or classmates ask questions
SPRINT 2 Wednesday group: 15/08 - 11/09 Thursday group: 16/08 - 12/09 Friday group: 17/08 - 13/09 | 18/08/2025 - 22/08/2025 | HTML, CSS | Workshop 2 (HTML, CSS) | 5
| 25/08/2025 - 29/08/2025 | 7.1. Modelo despliegue | Tarea 1: Realizar el diagrama de despliegue y registrarlo en la wiki. Tomar el diagrama de alto nivel como punto de partida. Tarea 2: Realizar el diagrama de componentes y registrarlo en la wiki. Tarea 3: Realizar el modelo de datos y registrarlo en la wiki. Tomar el modelo de dominio como punto de partida.
7.2. Modelo de componentes
7.3. Modelo de datos
Seguimiento a equipos - Backlog Sprint 2
| 01/09/2025 - 05/09/2025 | Seguimiento a equipos y trabajo en Entrega 2 | Deliverable 2: MVP, detailed architecture Plazo hasta el domingo, en la Wiki | 20
| 08/09/2025 - 12/09/2025 | Review Sprint 2 | Review 2
SPRINT 3 Wednesday group: 12/09 - 16/10 Thursday group: 13/09 - 17/10 Friday group: 14/09 - 18/10 | 15/09/2025 - 19/09/2025 | Analítica básica y/o LLMS | Workshop 3 (Analítica y/o LLMS) | 5
| 22/09/2025 - 26/09/2025 | Identidad de marca + UX | * Comercial: https://www.fastcompany.com/3058156/children-spend-less-time-outdoors-than-prisoners-according-to-new-persil-ad * Mal ejemplo de experiencia de usuario: https://userinyerface.com/ * Malos ejemplos de diseño en páginas web: https://www.allianceinteractive.com/blog/bad-websites-examples-worst-websites-designs-to-avoid/ * Buenos ejemplos de diseño en páginas web: https://www.softr.io/web-app/web-app-design-examples/ * Paleta de colores: https://color.adobe.com/es/create/color-wheel * Creación de logo: https://www.bing.com/images/create?FORM=BICMB1&ssp=1&darkschemeovr=0&setlang=es-CL&safesearch=moderate&toWww=1&redig=8195C3604CE2443CAD2B9B2FB3512087 Tarea: Crear el logo y el slogan. Incluir también la paleta de colores. Subir a la wiki.
| 29/09/2025 - 03/10/2025 | Seguimiento a equipos |  |  | Jornadas Universitarias. Lo más probable es que el jueves no haya actividades evaluativas y que el viernes no haya clase ni actividades evaluativas Sugerencia grupo jueves y grupo viernes: Dejar la entrega para el mismo día de la presentación.
| 06/10/2025 - 10/10/2025 |  |  |  | Se suspenden clases y actividades evaluativas
| 13/10/2025 - 17/10/2025 | Review Sprint 3 | Deliverable 3: More detailed architecture and new functions that provide additional value Review 3 | 20
SPRINT 4 Wednesday group: 17/10 - 13/11 Thursday group: 18/10 - 14/11 Friday group: 19/10 - 15/11 | 20/10/2025 - 24/10/2025 | Despliegue | Workshop 4 (Deployment) | 5
| 27/10/2025 - 31/10/2025 | Seguimiento a equipos
| 03/11/2025 - 07/11/2025 | Seguimiento a equipos | Deliverable 4: Final product with improvements and documentation Plazo hasta el domingo, en la Wiki | 20
Sustentaciones
| 10/11/2025 - 14/11/2025 | Sustentaciones | Review 4
| 17/11/2025 - 21/11/2025 |  | Review 4 (con autorización del profesor)
100
| 14/07/2025 - 08/11/2025 | Clases
| 06/10/2025 - 12/10/2025 | Receso
| 2025-09-02 | Asamblea general de carreras
| 29/09/2025 - 05/10/2025 | Jornadas universitarias
| 29/07/2025 - 09/11/2025 | Cancelación de asignaturas y semestre, sin derecho a devolución
| 2025-11-05 | Fecha límite para reportar las notas parciales y seguimientos correspondientes al 70% a través de Interactiva Virtual
| 10/11/2025 - 22/11/2025 | Evaluaciones finales
| 2025-11-25 | Fecha límite para el reporte de las notas correspondientes al 100% a través de Interactiva Virtual
| 26/11/2025 - 28/11/2025 | Balance académico